## Sheet1
Sprints | features | Tasks | Start | End | Days/hours | Who | State
| Project planning |  | 2018-07-03 | 2018-08-03 | 1 | Mohamed Salah | Done
| Scenario |  | 2018-07-03 | 2018-07-03 | 5 Hours | Seham Anwer | Done
| Requirment analysis |  | 2018-07-03 | 2018-08-03 | 1 | Esraa khtab | Done
| User Story |  | 2018-07-03 | 2018-08-03 | 1 | Hady Hamad | Done
| title&description |  | 2018-07-03 | 2018-07-03 | 8 Hours | Hader Mohamed | Done
| Schedule |  | 2018-07-03 | 2018-08-03 | 1 | Nada Abdullah | Done
Sprint 1 |  |  | 2018-08-03 | 15/3/2018 | 7 | All Team | Done
|  | Requirment gathering | 2018-08-03 | 2018-08-03 | 10 Hours | Hady Hamad | Done
|  | Design interface | 2018-08-03 | 2018-09-03 | 1 | Mohamed Salah | Done
| LOGIN | implementation Login page | 2018-09-03 | 2018-10-03 | 1 | Seham&Hadeer | Done
|  | Testing login page | 2018-10-03 | 2018-10-03 | 5 Hours | Esraa khtab | Done
|  | Create one tables in DB | 2018-10-03 | 2018-11-03 | 1 | Nada Abdullah | Done
|  | Requirment gathering | 2018-11-03 | 2018-11-03 | 10 Hours | Mohamed&seham | Done
|  | Design interface about Sign up page | 2018-11-03 | 2018-12-03 | 1 | Hady Hamad | Done
| Sign Up | implementation Sign up page | 2018-12-03 | 14/3/2018 | 1 | Esraa &nada | Done
|  | connect database with interface | 14/3/2018 | 14/3/2018 | 5 Hours | Nada Abdullah | Done
|  | Testing contact page | 14/3/2018 | 15/3/2018 | 1 | Hader Mohamed | Done
Sprint2 |  |  | 15/3/2018 | 28/3/2018 | 13 | All Team | Done
|  | Requirment gathering | 15/3/2018 | 15/3/2018 | 5 Hours | Hadeer | Done
|  | Design interface of About page | 15/3/2018 | 16/3/2018 | 8 Hours | Hady Hamad | Done
| About | implementation About page | 16/3/2018 | 17/3/2018 | 1 | salah&Esraa | Done
|  | Testing | 17/3/2018 | 17/3/2018 | 10Hourse | Nada Abdullah | Done
Done
|  | Requirment gathering | 17/3/2018 | 17/3/2018 | 7 hourse | Seham Anwer | Done
|  | Design filter method | 17/3/2018 | 18/3/2018 | 1 | Hady Hamad | Done
| Filter | implementation filter | 18/3/2018 | 20/3/2018 | 2 | Nada &seham | Done
|  | Testing filter | 20/3/2018 | 21/3/2018 | 1 | salah | Done
9j
|  | Requirment gathering | 21/3/2018 | 21/3/2018 | 9 hours | salah | in progress
|  | Design Contact page | 21/3/2018 | 22/3/2018 | 1 | hadeer | in progress
| Contact Us | implementation Contact | 22/3/2018 | 24/3/2018 | 2 | esraa&seham | in progress
|  | Testing contact page | 24/3/2018 | 25/3/2018 | 1 | hady | in progress
|  | create contact page data base | 25/3/2018 | 28/3/2018 | 3 | nada&hadeer | in progress
Mid term Exam |  |  | 29/3/2018 | 2018-04-04 | 8
sprint 3 |  |  | 2018-04-04 | 18/4/2018 | 7 | All Team | Not Started
|  | Requirment gathering | 2018-04-04 | 2018-04-04 | 10Hourse | Nada | Not Started
|  | Design Page contain film description | 2018-04-04 | 2018-05-04 | 1 | salah | Not Started
| film description | implementation page | 2018-05-04 | 2018-08-04 | 3 | hady&esraa | Not Started
|  | Testing | 2018-08-04 | 2018-08-04 | 12 hours | hadeer | Not Started
Not Started
|  | Requirment gathering | 2018-08-04 | 2018-09-04 | 1 | hady | Not Started
|  | Design Available cinema information | 2018-09-04 | 2018-11-04 | 2 | nada | Not Started
| Available Cinemas | implementation page | 2018-11-04 | 15/4/2018 | 4 | esraa&seham | Not Started
|  | Testing | 15/4/2018 | 17/4/2018 | 2 | salah | Not Started
sprint 4 |  |  | 17/4/2018 | 2018-01-05 | 14 | All Team | Not Started
|  | Requirment gathering | 17/4/2018 | 17/4/2018 | 7 hourse | seham | Not Started
| Booking | Design Booking page | 17/4/2018 | 19/4/2018 | 2 | Hader Mohamed | Not Started
|  | implementation Booking page | 19/4/2018 | 24/4/2018 | 5 | Mohamed Salah | Not Started
|  | Testing Booking Page | 24/4/2018 | 24/4/2018 | 10 Hours | hady | Not Started
|  | Create Project data Base | 24/4/2018 | 2018-01-05 | 7 | Nada Abdullah | Not Started