## Sheet1
Product BackLog
Task Name | Priority | Status | Assigned To | Active Sprint
Login
Requirment gathering for login page | High | Complete | Hady Hamad | 1
Design to login interface | High | Complete | Mohamed Salah | 1
implementation Login page (Coding It) | High | Complete | Seham&Hadeer | 1
Testing login page | Medium | Complete | Esraa khatab | 1
Create two tables in DB | High | Complete | Nada Abdullah | 1
Sign up
Requirment gathering from user | High | Complete | Mohamed&seham | 1
Design interface Sign up with us | Medium | Complete | Hady Hamad | 1
implementation Contact page (Coding It) | High | Complete | Esraa &nada | 1
Connect Data base with Interface | High | Complete | Nada Abdallah | 1
Testing contact page | Medium | Complete | Hader Mohamed | 1
About Us
Requirment gathering about needs to be in the Peofile | High | In Progress | Hadeer | 2
Design an interface for the User profile | High | In Progress | Hady Hamad | 2
implementation Account page (Coding It) | High | In Progress | salah&Esraa | 2
Testing | medium | In Progress | Nada Abdullah | 2
Filter
Requirment gathering for needs to be in the Filter feature | High | In Progress | Seham Anwer | 2
Design The Filter Method | High | In Progress | Hady Hamad | 2
implementation Filter Method | High | In Progress | Nada &seham | 2
Testing Filter | Medium | In Progress | salah | 2
Contact Us
Requirment gathering for the information needed | Medium | In Progress | salah | 2
Design The Interface and ways to show this information | High | In Progress | hadeer | 2
implementation Contact us page | Low | In Progress | esraa&seham | 2
Testing This Page | Low | In Progress | hady | 2
Film descrptions
Requirment gathering about the details of films | High | Not Started | Nada | 3
Design The short way to show the main describtions of the film | medium | Not Started | salah | 3
implementation Descriptions page | medium | Not Started | hady&esraa | 3
Testing Film Description page | medium | Not Started | hadeer | 3
Avaliable Cinema
Requirment gathering about the cinema and its location | High | Not Started | hady | 3
Design interface of the avaliable cinema and its Location | medium | Not Started | nada | 3
implementation Avaliable Cinema Page | High | Not Started | esraa&seham | 3
Testing Avaliable Cinema Page | Low | Not Started | salah | 3
Booking
Requirment gathering about The Technique to pay to booking this film. | High |  | seham | 4
Design interface to facilitate the way to booking | High |  | Hader Mohamed | 4
implementation The Different Methods To Booking | High |  | Mohamed Salah | 4
Testing The Booking Page | High |  | hady | 4
Create The whole Project DataBase | High |  | Nada Abdullah | 4