## Sheet1
Backlog
# | Item
1 | Requirement gathering for login page
2 | Design login page
3 | Build login page
4 | Test login page
5 | Create one table in database
6 | Requirement gathering for sign up page
7 | Design sign up page
8 | Build sign up page
9 | Test sign up page
10 | Connect the database with interface
11 | Integration phase 1
12 | Demo phase 1
13 | Requirement gathering for about page
14 | Design interface for about page
15 | Build about page
16 | Test about page
17 | Requirement gathering for filter page
18 | Design filter page
19 | Build filter page
20 | Test filter page
21 | Requirement gathering for contact us page
22 | Design contact us page
23 | Build contact us page
24 | Test contact us page
25 | Integration phase 2
26 | Demo phase 2
27 | Requirement gathering for film description page
28 | Design film description page
29 | Build film description page
30 | Test film description page
31 | Requirement gathering for avaliable cinemas page
32 | Design film avaliable cinemas page
33 | Build film avaliable cinemas page
34 | Test avaliable cinemas page
35 | Integration phase 3
36 | Demo phase 3
37 | Requirement gathering for Booking page
38 | Design Booking page
39 | Build Booking page
40 | Test Booking page
41 | Create a project database
42 | Integration phase 4
43 | Full system integration