## Sheet1
Sprint 1(Login & Contact Us Pages
| Sprint 1 (Create Login Page) | [10 empty] | Sprint 1 (Contact us Page)
Tasks |  | Start | End | Days/Hours |  |  | Who ? |  | Priority | Status | Tasks |  | Start | End |  | Days/Hours | Who ? |  | Priority | Status
Requirment gathering |  | 2018-03-08 | 2018-03-08 | 10 Hours |  |  | Hady Hamad |  | High | Complete | Requirment gathering |  | 2018-11-03 | 2018-11-03 |  | 10 Hours | Mohamed&seham |  | High | Complete
Design interface |  | 2018-03-08 | 2018-03-09 | 1 |  |  | Mohamed Salah |  | Medium | Complete | Design interface |  | 2018-11-03 | 2018-12-03 |  | 1 | Hady Hamad |  | Medium | Complete
implementation Login page |  | 2018-03-09 | 2018-03-10 | 1 |  |  | Seham&Hadeer |  | High | Complete | implementation Login page |  | 2018-12-03 | 14/3/2018 |  | 1 | Esraa &nada |  | High | Complete
Testing login page |  | 2018-03-10 | 2018-03-10 | 5 Hours |  |  | Esraa khtab |  | Low | Complete | Testing login page |  | 14/3/2018 | 15/3/2018 |  | 5 Hours | Hader Mohamed |  | Low | Complete
Create two tables in DB |  | 2018-03-10 | 2018-03-11 | 1 |  |  | Nada Abdullah |  | Low | Complete
Sprint 2(Account Profile & Filter &Information about Films)
| Sprint 2 (About Us ) | [11 empty] | Sprint 2 (Filter ) | [8 empty] | Sprint 2 (Information About films )
Tasks |  | Start | End | Days/Hours |  |  | Who ? |  | Priority | Status | Tasks |  | Start | End | Days/Hours |  | Who ? | Priority |  | Status | Tasks | Start | End | Days/Hours | Who ? | Priority | Status
Requirment gathering |  | 15/3/2018 | 15/3/2018 | 5 Hours |  | 5 Hours | Hadeer Mohamed | Hadeer | High | In Progress | Requirment gathering |  | 16/3/2018 | 16/3/2018 | 7 hourse |  | Seham Anwer | High |  | In Progress | Requirment gathering | 18/3/2018 | 18/3/2018 | 9 hours | Seham Anwer | High | In Progress
Design interface of Profile page |  | 15/3/2018 | 15/3/2018 | 8 Hours |  | 8 Hours | Hady Hamad | Hady Hamad | Medium | In Progress | Design filter method |  | 16/3/2018 | 16/3/2018 | 6 hourse |  | Hady Hamad | Medium |  | In Progress | Design information page | 18/3/2018 | 19/3/2018 | 1 | Hady Hamad | Medium | In Progress
implementation profile page |  | 15/3/2018 | 16/3/2018 | 1 |  | 1 | salah&Esraa | salah&Esraa | High | In Progress | implementation filter |  | 16/3/2018 | 18/3/2018 | 2 |  | Nada &seham | High |  | In Progress | implementation filter | 19/3/2018 | 21/3/2018 | 2 | Nada &seham | High | In Progress
Testing |  | 16/3/2018 | 16/3/2018 | 10Hourse |  | 10Hourse | Nada Abdullah | Nada Abdullah | Low | In Progress | Testing filter |  | 18/3/2018 | 18/3/2018 | 10 Hours |  | salah | Low |  | In Progress | Testing | 21/3/2018 | 22/3/2018 | 1 | salah | Low | In Progress
Sprint 3(film description&Available Cinemas)
| Sprint 3 (film description ) | [11 empty] | Sprint 3 (Available Cinemas )
Tasks |  | Start | End | Days/Hours |  |  | Who ? |  | Priority | Status | Tasks |  | Start | End | Days/Hours |  | Who ? |  | Priority | Status
Requirment gathering |  | 22/3/2018 | 22/3/2018 | 10Hourse |  | 5 Hours | Nada | Hadeer | High | Not Started | Requirment gathering |  | 25/3/2018 | 25/3/2018 | 10 Hours |  | hady |  | High | Not Started
Design Page contain film description |  | 22/3/2018 | 23/3/2018 | 1 |  | 8 Hours | salah | Hady Hamad | Medium | Not Started | Design Available cinema information |  | 25/3/2018 | 26/3/2018 | 1 |  | nada |  | Medium | Not Started
implementation page |  | 23/3/2018 | 25/3/2018 | 2 |  | 1 | hady&esraa | salah&Esraa | High | Not Started | implementation page |  | 26/3/2018 | 28/3/2018 | 2 |  | esraa&seham |  | High | Not Started
Testing |  | 25/3/2018 | 25/3/2018 | 12 hours |  | 10Hourse | hadeer | Nada Abdullah | Low | Not Started | Testing |  | 28/3/2018 | 29/3/2018 | 1 |  | salah |  | Low | Not Started
Sprint 4(Booking )
Sprint 4 (Booking )
Tasks |  | Start | End | Days/Hours |  |  | Who ? |  | Priority | Status
Requirment gathering |  | 29/3/2018 | 29/3/2018 | 7 hourse |  | 5 Hours | seham | Hadeer | High | Complete
Design Booking page |  | 29/3/2018 | 30/3/2018 | 1 |  | 8 Hours | Hader Mohamed | Hady Hamad | Medium | Complete
implementation Booking page |  | 30/3/2018 | 2018-01-04 | 2 |  | 1 | Mohamed Salah | salah&Esraa | High | Complete
Testing Booking Page |  | 2018-01-04 | 2018-01-04 | 10 Hours |  | 10Hourse | hady | Nada Abdullah | Low | Complete
Create Project data Base |  | 2018-01-04 | 2018-05-04 | 5 |  |  | Nada Abdullah |  | Low | Complete

## Sheet2
High | Complete
Medium | In Progress
Low | Not Started